| WRECKIT 2015 Regional Scenario and days of play | Hospital Scenario and activities by days of play Hospital personalizes this to their play | Planning Follow-up Hospital personalizes this to their play |
| --- | --- | --- |
| - [Can use Mid-Planning Conference PP] - WRECKIT-Western Region Emergency Communications Knowledge and Information Tests - Ice storm scenario with impacts over the 17 county region. Communications and utility outages, impacts to healthcare facilities will occur. - Regional exercise days will be October 5-9. Some off-week events will also occur; September 10th is a Cross-border PA Tabletop exercise for the S. Tier counties. - Multiple agencies are currently engaged on the federal, state, regional, local level. Government, private (health sector, food service industry). About 400 agencies at this point. - Breakdown of scenario by day. Certain activities are planned to include all hospitals in the region. - Monday 10/5- Blue sky day. Weather event forecasted by National Weather Service (NWS). Agencies anticipate the arrival and impacts of the storm. All hospitals respond to a HAvBED. - Tuesday 10/6- Weather event “hits”. NWS calls for county emergency management; full scale and functional play at agencies and regionally. An exercise simulation cell will be activated to simulate agencies not in play. - This will likely be the day when most hospital command centers will be activated in WNY. - Several events are planned that hospitals will need to respond to on this day. See 1-6 - Wednesday 10/7- weather event continues, agency and regional play, simcell active. - Thursday 10/8- Regional table-top exercises; AM-Road closures Tabletop Exercise (TTEx); PM-Sheltering TTEx. - Friday 10/9- After-action conference, time and location-TBA | - This is a collaborative and coalition based activity that can drive can drive anything we need to test. - Hospital activities will focus on testing of___________ and participation in the exercise on specific days. - Hospital days of play described. - Monday 10/5. - PM, HAvBED survey - Additional Hospital-planned activities - Tuesday 10/6. - HCC will be activated. - Hospital will respond to regional events: - HAvBED survey - WNY Hospital Mutual Aid Plan activation and requests - Hospital Status Field Report submission - Alternate communications methods - Optional- eFINDS receiving from Test hospital. - A pediatric mass casualty-surge event will impact two hospitals in the WNY S. Tier - Hospital submits a request for Strategic National Stockpile assets to their Local Health Department/ per county plan - Additional Hospital-planned activities here - Wednesday 10/7. - AM- Interoperable communications testing - Optional-return patients to Test hospital in eFINDS - 1:00 PM- ESF-8/ Health Desk Work Shop at the ECFTF - Additional Hospital planned activities | - Develop Org Chart for the HCC - Review staff in HAvBED and eFINDS roles, have active HCS accounts - Discuss alternate communications methods to be tested. - Discuss if eFINDS receiving will be tested. - Discuss days of active play. |
| - General Objectives for WRECKIT The key objective is to assess how we gain, maintain, and assess situational awareness; and share information within and across agencies. - Gain, maintain and assess situational awareness - Activate Operation/Command Centers - Mass care for first 48 hours - Resource management - Volunteer coordination | - Hospital Objectives. OHEP required objectives and critical tasks are attached. - Additional hospital objectives: - Determine additional plans to be tested and days they will be tested. | Decide what hospital-specific activities will occur on days of play. |
| Participating & Coordinating Agencies - WNY hospitals; most full-scale activities will be 10/6 - Local Health Departments (days vary ; 10/7) - NYSDOH WR Health Operations Center, 10/6 - WNY Hospital MAP, 10/6 - WNY LTC MAP, 10/7 - State EOC (bunker), 10/6 - Some OEMs, dates vary - NWS, 10/6 & 10/7 - NYS Department of Transportation | Hospital Participants and Departments - Discuss information that can be shared with players by planning team/ trusted agents. - Is pre-exercise training needed ? | - Inform Administration, participants, Departments on expectations for play and days of play. - Schedule training if needed. |
| - Exercise Design. Hospital exercise will flow from the generic Hospital ExPlan and WRECKIT scenario. The hospital is required to meet objectives provided by NYSDOH OHEP in order to voucher $14,000. $8,000 for Planning ; $6,000 for participation. | Hospital must submit the following for EP Grant payment: Planning: - Documentation that summarizes the exercise planning. Activities, including planning session date(s), summary of topics discussed, attendees (names/titles) and their exercise role(s). Participation: - Exercise HSEEP compliant Exercise Evaluation Guide (EEG) and a completed NYSDOH “Quick Look” evaluation summary document. | Ensure sign-in sheets and documentation conforms to OHEP requirements |
| - Documentation provided by WRECKIT planning - ExPlan, C/E Handbook, Exercise Evaluation Guides (EEGs) - Required Objectives - Critical Tasks to meet hospital objectives - Master Scenario Events List (MSEL) - Planning Conférence Sign-in sheets - Exercise Participation Sign-in sheets - NYSDOH evaluation summary document | - Hospital modifies documents to reflect internal planning - ExPlan Objectives - Exercise Schedule, Master Scenario Events List - Exercise Evaluation Guides |  |
| - Evaluation - Sources for controllers/ evaluators - Exercise Evaluation Guides | - Determine if the hospital has trained HSEEP trained evaluators - Request external evaluator from WRECKIT Planning - Modify EEG critical tasks to hospital exercise | Identify HSEEP-trained evaluator (internal or provided by WRECKIT planning) |
| - Support Requirements - Actors? |  |  |
| - Next Steps- Exercise date |  |  |