WRECK IT 2015

Western Region RACES –ARES Exercise Plan

August, 2015

Version 7/29/15 1630

# Exercise Overview

| Exercise Name | This ExPlan covers the off-schedule component of the exercise Western Region Emergency Communications, Knowledge, and Information Tests (WRECK IT) 2015 called “WRECKIT 2015 Western Region (WR) Radio Amateur Civil Emergency Services (RACES) –Amateur Radio Emergency Services (ARES) Exercise”, also known as WR RACES-ARES Exercise 2015. |
| --- | --- |
| Exercise Dates | WR RACES –ARES Exercise is scheduled on August 8, 2015. The exercise is planned for three hours from 0900 – 1200. |
| Scope | This exercise includes operations-based communications testing activities using amateur radios at WR hospital and actual or simulated county Offices of Emergency Management in participating counties in the Western Region (WR) of New York State. |
| Mission Area(s) | Response |
| Core Capabilities | Community/Healthcare Preparedness, Emergency Operations Coordination, Information Sharing |
| Objectives | - Assess the ability of regional partners to receive and disseminate information related to an upcoming weather event within their agency and jurisdiction. - Assess the ability of regional partners to receive and disseminate information using alternate, interoperable communications methods. - Test the ability to transmit messages via verbal and/or data communications modes for amateur radio. - Assess agency-owned equipment status. - Asses the capability and tools used in sharing current status reports with local and regional partners. - Test the hospital’s ability to complete the draft Hospital Field Report Form and solicit feedback on the utility of the form’s information to hospitals. - Test the ability to transmit the hospital’s completed Hospital Field Report Form with formatting intact via verbal and data modes between agencies. |
| Threat or Hazard | Significant Winter Storm/Ice Storm |
| Scenario | An early winter storm is predicted to hit Western New York that begins with greater than ½ inch and greater of ice accumulation followed by several days to below freezing temperatures and wind chill temperatures of below zero. Communications outages related to the weather situation are actual and anticipated in areas of the Western Region. |
| Sponsor | New York State Department of Health (NYSDOH), Office of Health Emergency Preparedness (OHEP), New York State Division of Homeland Security and Emergency Services (NYS DHSES), Office of Emergency Management (SOEM). |
| Participating Organizations | Federal, State, Regional, and local partners in Western New York. The full list of participating agencies in Appendix B. |
| Point of Contact | WRECK-IT e-mail wreckit2015@gmail.com Diana Volkman 716-481-9735 diana.volkman@health.ny.gov Joseph Indelicato 585-423-8187 cell 716-698-9227 Joseph.indelicato@health.ny.gov KC2TNH Patrick Byrne, NYSDOH, OHEP. 335 E Main St, Rochester, NY 14604. patick.byrne@health.ny.gov. 585-423-8066 |
| Regional Design Team | Scott Barry, RPA, WNY/GR/ST LTC Mutual Aid Plans Patrick Byrne, NYSDOH, OHEP FL William Correa, NYSDHES, SOEM Region V FL Zone Anne D’Angelo, Finger Lakes RTC Michael Devries, NYSP, FL Zone Stacy Forenz, NYSDOT Region 6 Joseph Indelicato, NYSDOH HAN IT Specialist Rich Jones, NYSDOT Region 4 Judy Levan, NWS Buffalo Nicholas MacVie, NYSDHES, SOEM Region V WNY Zone David Nicosia, NWS Binghamton Deborah Palumbos, RRHA Eileen Spezio, Finger Lakes RTC Diana Volkman, NYSDOH, OHEP WNY Lynnette Ward, EP Coordinator FF Thompson Hospital |

# General Information

## Exercise Objectives and Core Capabilities

The following exercise objectives in Table 1 describe the expected outcomes for the exercise.  The objectives are linked to core capabilities, which are distinct critical elements necessary to achieve the specific mission area(s).  The objectives and aligned core capabilities are guided by elected and appointed officials and selected by the Exercise Planning Team.

| Exercise Objective | Core Capability |
| --- | --- |
| - Assess the ability of regional partners to receive and disseminate information related to an upcoming weather event within their agency and jurisdiction. - Assess the ability of regional partners to receive and disseminate information using alternate, interoperable communications methods. - Test the ability to transmit messages via verbal and/or data communications modes for amateur radio. - Assess agency-owned equipment status. - Asses the capability and tools used in sharing current status reports with local and regional partners. - Test the hospital’s ability to complete the draft Hospital Field Report Form and solicit feedback on the utility of the form’s information to hospitals. - Test the ability to transmit the hospital’s completed Hospital Field Report Form with formatting intact via verbal and data modes between agencies. | Community/Healthcare Preparedness Emergency Operations Coordination Information Sharing |

Table 1. Exercise Objectives and Associated Core Capabilities

## Participant Roles and Responsibilities

The term participant encompasses many groups of people, not just those playing in the exercise.  Groups of participants involved in the exercise, and their respective roles and responsibilities, are as follows:

- Players.  Players are personnel who have an active role in discussing or performing their regular roles and responsibilities during the exercise.  Players discuss or initiate actions in response to the simulated emergency.

- Controllers.  Controllers plan and manage exercise play, set up and operate the exercise site, and act in the roles of organizations or individuals that are not playing in the exercise.  Controllers direct the pace of the exercise, provide key data to players, and may prompt or initiate certain player actions to ensure exercise continuity.  In addition, they issue exercise material to players as required, monitor the exercise timeline, and supervise the safety of all exercise participants.

- Simulators.  Simulators are control staff personnel who role play nonparticipating organizations or individuals.  Some county Offices of Emergency Management may be simulated at an off-site location by RACES-ARES operators in order to allow hospitals to pass message traffic according to the exercise design. This portion of the WRECKIT 2015 Exercise will not use a central Simcell.

- Evaluators.  Evaluators evaluate and provide feedback on a designated functional area of the exercise.  Evaluators observe and document performance against established capability targets and critical tasks, in accordance with the Exercise Evaluation Guides (EEGs).

- Observers.  Observers visit or view selected segments of the exercise.  Observers do not play in the exercise, nor do they perform any control or evaluation functions.  Observers view the exercise from a designated observation area and must remain within the observation area during the exercise.

- Media Personnel.  Some media personnel may be present as observers, pending approval by the participating agency.

- Support Staff.  The exercise support staff includes individuals who perform administrative and logistical support tasks during the exercise (e.g., registration, catering).

## Exercise Assumptions and Artificialities

In any exercise, assumptions and artificialities may be necessary to complete play in the time allotted and/or account for logistical limitations.  Exercise participants should accept that assumptions and artificialities are inherent in any exercise, and should not allow these considerations to negatively impact their participation.

### Assumptions

Assumptions constitute the implied factual foundation for the exercise and, as such, are assumed to be present before the exercise starts.  The following assumptions apply to the exercise:

- The exercise is conducted in a no-fault learning environment wherein capabilities, plans, systems, and processes will be evaluated.

- The exercise scenario is plausible, and events occur as they are presented.

- Exercise simulation contains sufficient detail to allow players to react to information and situations as they are presented as if the simulated incident were real.

- Participating agencies may need to balance exercise play with real-world emergencies.  Real-world emergencies take priority.

### Artificialities

During this exercise, the following artificialities apply:

- Exercise communication and coordination is limited to participating exercise organizations, venues, and the SimCell.

- Communication methods listed in the WRECKIT 2015 RACES-ARES Exercise Communications Directory are available for players to use during the exercise.

# Exercise Logistics

## Safety

Exercise participant safety takes priority over exercise events.  The following general requirements apply to the exercise:

- A Safety Controller is responsible for participant safety; any safety concerns must be immediately reported to the Safety Controller.  The Safety Controller and Exercise Director will determine if a real-world emergency warrants a pause in exercise play and when exercise play can be resumed.

- For an emergency that requires assistance, use the phrase “real-world emergency.”  The following procedures should be used in case of a real emergency during the exercise:

- Anyone who observes a participant who is seriously ill or injured will immediately notify emergency services and the closest controller, and, within reason and training, render aid.

- The controller aware of a real emergency will initiate the “real-world emergency” broadcast and provide the Safety Controller, Senior Controller, and Exercise Director with the location of the emergency and resources needed, if any.  The Senior Controller will notify the SimCell as soon as possible if a real emergency occurs.

## Site Access

### Security

If entry control is required for the exercise venues, the participating agency is responsible for arranging appropriate security measures.  To prevent interruption of the exercise, access to exercise sites is limited to exercise participants.  Players should advise their agency controller or evaluator of any unauthorized persons.

### Media/Observer Coordination

Agencies with media personnel and/or observers attending the event should plan for controlled access to the exercise site.  Media/Observers may be escorted to designated areas and should be accompanied by an exercise controller at all times.  Sponsor organization representatives and/or the observer controller may be present to explain exercise conduct and answer questions.  Exercise participants should be advised of media and/or observer presence.

### Exercise Identification

For the exercise, operators reporting to hospital and Emergency Operations sites should have valid identification such as RACES/ ARES identification, or a Driver’s License, and should wear their RACES/ARES credential if available. Exercise staff may be assigned by their site to wear role-specific identification including badges, hats, and/or vests to clearly display exercise roles; uniform clothing may be worn to show agency affiliation.  Other than the RACES-ARES credential and hospital identification, no specific garb has been identified by the Exercise Planning Team for this exercise. Onsite point of contact personnel should introduce themselves to their assigned operator and provide any identification required by the agency.

# Post-exercise and Evaluation Activities

## Debriefings

Post-exercise debriefings aim to collect sufficient relevant data to support effective evaluation and improvement planning.

### Hot Wash

At approximately 11:30 AM on August 8th at the conclusion of exercise play, the exercise controllers will facilitate a conference call/ webinar Hot Wash to allow players to discuss strengths and areas for improvement, and evaluators to seek clarification regarding player actions and decision-making processes.  All participants may attend; however, observers are not encouraged to attend the meeting.  The Hot Wash should not exceed 30 minutes.

The Hotwash Conference webinar- call-in numbers:

Meeting Number: 643 362 488

Meeting Password: wreckit2015 
https://meetny.webex.com/meetny/j.php?MTID=mcd0fbfab5413476808e8788e8c9317cd 
Local: 1-518-549-0500 Toll Free: 1-844-633-8697 1-866-776-3553

### Controller and Evaluator Debriefing

Controllers and evaluators may attend a facilitated C/E Debriefing immediately following the exercise if scheduled by the participating agency to provide an overview of their observed functional areas and discuss strengths and areas for improvement.

## Evaluation

### Exercise Evaluation

The evaluation provides players with the opportunity to comment candidly on exercise activities and exercise design.  Evaluation feedback from all exercise participants will be collected via an online survey. The link to the survey is https://www.surveymonkey.com/s/ZM93X69. All participants are asked to complete applicable portions of the survey following the exercise as soon as possible to capture critical information from the exercise that will be included in the exercise After Action Report (AAR).

### After-Action Report

The AAR summarizes key information related to evaluation.  The AAR primarily focuses on the analysis of core capabilities, including capability performance, strengths, and areas for improvement.  AARs also include basic exercise information, including the exercise name, type of exercise, dates, location, participating organizations, mission area(s), specific threat or hazard, a brief scenario description, and the name of the exercise sponsor and POC.  Findings including strengths and improvements from the RACES-ARES Exercise will be incorporated to the WRECKIT 2015 AAR.

## Improvement Planning

Improvement planning is the process by which the observations recorded in the AAR are resolved through development of concrete corrective actions, which are prioritized and tracked as a part of a continuous corrective action program.

### Improvement Plan

The IP identifies specific corrective actions, assigns them to responsible parties, and establishes target dates for their completion.  It is created by elected and appointed officials from the organizations participating in the exercise.

# Participant Information and Guidance

## Exercise Rules

The following general rules govern exercise play:

- Real-world emergency actions take priority over exercise actions.

- Exercise players will comply with real-world emergency procedures, unless otherwise directed by the control staff.

- All communications (including written, radio, telephone, and e-mail) during the exercise will begin and end with the statement “This is an exercise.”

- Exercise players who place telephone calls or initiate radio communication must identify the organization or individual with whom they wish to speak.

## Players Instructions

Players should follow certain guidelines before, during, and after the exercise to ensure a safe and effective exercise.

### Before the Exercise

- Review appropriate organizational plans, procedures, and exercise support documents.

- Hospitals should complete the Hospital Field Status Report Form and email it to WRECKIT2015@gmail.com by Wednesday August 5, 2015. Hospitals are also requested to provide the form to their operator or county RACES Coordinator contact at that time.

- On exercise day, be at the appropriate site at least 30 minutes before the exercise starts at 0900 on Saturday, August 8, 2015.  Bring the appropriate identification item(s), including RACES-ARES credential, if available.

- Follow the procedure at your site to check-in. At hospitals, operators should request to see the point of contact identified for the site in the exercise Communications Directory.

### During the Exercise

- Respond to exercise events and information as if the emergency were real, unless otherwise directed by an exercise controller.

- Controllers will give you only information they are specifically directed to disseminate.  You are expected to obtain other necessary information through existing emergency information channels.

- Do not engage in personal conversations with controllers, evaluators, observers, or media personnel.  If you are asked an exercise-related question, give a short, concise answer.  If you are busy and cannot immediately respond, indicate that, but report back with an answer as soon as possible.

- If you do not understand the scope of the exercise, or if you are uncertain about an organization’s participation in an exercise, ask a controller.

- Parts of the scenario may seem implausible.  Recognize that the exercise has objectives to satisfy and may require incorporation of unrealistic aspects.  Every effort has been made by the exercise’s trusted agents to balance realism with safety and to create an effective learning and evaluation environment.

- All exercise communications will begin and end with the statement “This is an exercise.”  This precaution is taken so that anyone who overhears the conversation will not mistake exercise play for a real-world emergency.

- When you communicate, identify the organization or individual with whom you wish to speak.

- Maintain a log of your activities and communications.  Note any difficulties or successes for future review.

### After the Exercise

- Participate in a Hot Wash at your venue with controllers and evaluators, if offered; and in the regional Hotwash.

- Complete the online evaluation survey. https://www.surveymonkey.com/s/ZM93X69

- If you have any additional information or comments you may send them to WRECKIT2015@gmail.com.

## Simulation Guidelines

Because the exercise is of limited duration and scope, certain details will be simulated.  The physical description of what would fully occur at the incident sites and surrounding areas may be relayed to players by simulators or controllers.  The roles and interactions of nonparticipating organizations such as non-participating Offices of Emergency Management and non-activated Emergency Operations sites may be simulated by operators onsite or offsite.

# Appendix A:  Exercise Schedule

Note:  Because this information is updated throughout the exercise planning process, appendices may be developed and updated as stand-alone documents rather than part of the ExPlan.

| Date | Time | Activity | Location |
| --- | --- | --- | --- |
| RACES-ARES Exercise and Pre-Exercise Activities |  |  |  |
| Date | Time | Action | Location |
| March 18, 2015 |  | WNY WRECKIT 2015 Initial Planning Conference (IPC) | Erie County Fire Training Facility (ECFTF) |
| March 22, 2015 |  | WNY WRECKIT 2015 Finger Lakes (FL) IPC | U of R/St. Joseph’s of Elmira |
| June 17, 2015 |  | WNY Mid-Planning Conference (MPC) | ECFTF |
| June 22, 2015 |  | FL MPC | U of R/St. Joseph’s of Elmira |
| July 1, 2015 | 1530-1630 | RACES/ARES Regional Exercise IPC | Webinar |
| July 22, 2015 | 1330-1430 | WRECKIT 2015 Exercise Design Call with hospitals for RACES/ARES Exercise | Webinar |
| July 22, 2015 | 1530-1630 | RACES/ARES Regional Exercise MPC | Webinar |
| August 4, 2015 | 1530-1630 | RACES/ARES Regional Exercise Final Planning Conference (FPC) Webinar-call | https://meetny.webex.com/meetny/j.php?MTID=m688cddbb43365168fe4b6a880e5f43c4 Meeting ID: 641 010 463 Password: wreckit2015 To join the audio conference only Local: 1-518-549-0500 Toll Free: 1-844-633-8697 1-866-776-3553 |
| August 5, 2015 |  | Hospitals must submit their completed Hospital Field Status Form to the Exercise e-mail account. A copy of this form must be available on August 8th for the operators. | Submit via email in PDF form to wreckit2015@gmail.com |
| August 8, 2015 | 0800-0830 | RACES/ARES Operators arrive at Exercise sites | See Appendix B |
| August 8, 2015 | 0830-1200 | Conference for support during exercise and Hot Wash post Exercise | Meeting Number: 643 362 488 Meeting Password: wreckit2015 https://meetny.webex.com/meetny/j.php?MTID=mcd0fbfab5413476808e8788e8c9317cd Local: 1-518-549-0500 Toll Free: 1-844-633-8697 1-866-776-3553 |
| August 8, 2015 | 0900 – 1100 | RACES-ARES Regional Exercise communications exercise commences | See Appendix B |
| August 8, 2015 | 1130-1200 | RACES/ARES Regional Exercise Hotwash Conference Call- all participants | Meeting Number: 643 362 488 Meeting Password: wreckit2015 https://meetny.webex.com/meetny/j.php?MTID=mcd0fbfab5413476808e8788e8c9317cd Local: 1-518-549-0500 Toll Free: 1-844-633-8697 1-866-776-3553 |
| August 8-13, 2015 |  | EOC Operators/ County Coordinators email Hospital Field Report forms in PDF as received to WRECKIT email | Email to WRECKIT2015@gmail.com |
| August 8-13, 2015 |  | All Participants Submit Evaluation | Complete online Survey https://www.surveymonkey.com/s/ZM93X69 |
| The following events are not required attendance and are part of the overall scenario. |  |  |  |
| September 10, 2015 | 0900 - 1200 | NY/PA Cross Boarder Issues Tabletop Ex | Alfred University |
| September 23, 2015 |  | WNY FPC | ECFTF |
| September 28, 2015 |  | FL FPC | U of R/St. Joseph’s of Elmira |
| WRECKIT 2015 Exercise Week |  |  |  |
| Date | Time | Action | Location |
| October 2, 2015 | 0930 | NWS Weather Warning |  |
| October 5, 2015 | 0845 | STARTEX |  |
| October 5, 2015 | 0900 | NWS Buffalo Conference Call |  |
| October 5, 2015 | 0930 | NWS Binghamton Conference Call |  |
| October 6, 2015 | 0800 | STARTEX |  |
| October 6, 2015 | 0800 | SimCell Activates |  |
| October 6, 2015 | 0900 | NWS Buffalo Conference Call |  |
| October 6, 2015 | 0930 | NWS Binghamton Conference Call |  |
| October 6, 2015 | 1600 | SimCell Deactivates |  |
| October 7, 2015 | 0800 | STARTEX |  |
| October 7, 2015 | 0800 | SimCell Activates |  |
| October 7, 2015 | 1600 | SimCell Deactivates |  |
| October 8, 2015 | 0900 | Major Road Closure TTx |  |
| October 8, 2015 | 1300 | Regional Sheltering Needs TTx |  |
| October 9, 2015 | 0930 | WRECK IT After Action Meeting |  |
| Post Exercise |  |  |  |
| December 11, 2015 |  | AAR/IP distributed for review |  |
| December 30, 2015 |  | AAR/IP comments due back |  |
| January 8, 2016 |  | Final AAR/IP distributed |  |

Appendix B:  RACES-ARES Exercise Participants

Participating Organizations in August 8,2015 Exercise

State

New York State Department of Health

New York State Office of Emergency Management

Regional

Western Region Healthcare Emergency Preparedness Coalition

Allegany County

Jones Memorial Hospital

Office of Emergency Management

Cattaraugus County

Olean General Hospital

Chautauqua County

Brooks Memorial Hospital

Emergency Services

Lake Shore Hospital

Westfield Memorial Hospital

WCA Hospital

Chemung County

Chemung County Emergency Management Office

Arnot Ogden

St. Joseph’s Hospital

Genesee County

Emergency Management Services

United Memorial Medical Center

Livingston County

Office of Emergency Management

Nicholas Noyes Memorial Hospital

Monroe County

Highland Hospital

Office of Emergency Management

Rochester General Hospital

Unity Health

University of Rochester Medical Center, Strong Memorial Hospital

Ontario County

Clifton Springs Hospital and Clinic

Emergency Management

FF Thompson Hospital

Geneva General Hospital

Schuyler County

Emergency Management Office

Schuyler Hospital

Steuben County

Guthrie Corning Hospital

Ira Davenport Memorial Hospital

Office of Emergency Services

Wayne County

Department of Emergency Management

Newark Wayne Community Hospital

Yates County

Department of Emergency Management

Soldiers and Sailors Hospital

# Appendix C:  RACES-ARES Exercise Communications Plan

Exercise Points of Contact

See Excel “Points of Contact/ Communications Directory” for sites/ agency points of contact.

ARES-RACES Communications Exercise Sequence

- By August 5th all hospitals must submit their completed Hospital Field Status Form to the exercise e-mail account at WRECKIT2015@gmail.com.  A copy of this form must be made available to the operator prior to or on August 8th. Hospitals are encouraged to work with their operator or county RACES Coordinator.

- August 8th, 0830, operators arrive onsite at hospitals and county OEM/ EOC actual and simulated locations, meet site point of contact if applicable, provide credentials, access site equipment or the area for equipment set-up, if using their own.

- If possible, and if needed, sites may log into the Web Conference for support and communication during the exercise.

  - Meeting Number: 643 362 488  Meeting Password: wreckit2015 
https://meetny.webex.com/meetny/j.php?MTID=mcd0fbfab5413476808e8788e8c9317cd 
Local: 1-518-549-0500 Toll Free: 1-844-633-8697 1-866-776-3553

- Equipment set-up and activation commences.

- The Hospital Field Report is provided to the operator by the hospital contact (if not previously provided).

- 0900, message traffic will commence as soon as sites within the county are determined ready and available by the county lead.

- 0900 – 1100, the Field Report provided by the hospital is transmitted exactly as formatted from the hospital to the local Office of Emergency Management (OEM)/ EOC actual or simulated site. The report must arrive in the EOC in PDF or printed form.

  - Band usage and details of transmission to be used as determined by operators and county coordinator

  - Digital and/ or verbal modes will be used as decided upon by the county RACES Coordinator according to the capabilities of the site and personnel.

  - Hospital equipment should be used if possible.

- Other message traffic may be transmitted between agencies testing digital and/or verbal modes and ICS forms until the exercise conclusion at 11:00; or until the county RACES Coordinator or lead designee deems the exercise objectives have been met.

- 11:30: Conference call Hotwash.

  - Meeting Number: 643 362 488  Meeting Password: wreckit2015 
https://meetny.webex.com/meetny/j.php?MTID=mcd0fbfab5413476808e8788e8c9317cd 
Local: 1-518-549-0500 Toll Free: 1-844-633-8697 1-866-776-3553

- Complete the evaluation survey as soon as possible at https://www.surveymonkey.com/s/ZM93X69

- As soon as possible after the exercise, EOC Operators/ County Coordinators email Hospital Field Report forms in PDF as received to WRECKIT email.

- Transmission from the county EOC sites to a Regional Net control may be trialed, if possible at the decision of the county coordinator. The Web Conference may be used for coordination of this effort.

03995.0 Lower Sideband for Monroe County Inter County communications.

# Appendix E:  Acronyms

| Acronym | Term |
| --- | --- |
| AAM | After Action Meeting |
| AAR/IP | After Action Report/Improvement Plan |
| ARES | Amateur Radio Emergency Services |
| C/E | Controller/Evaluator |
| ECFTF | Erie County Fire Training Facility |
| EEG | Exercise Evaluation Guides |
| EOC | Emergency Operations Center |
| EP | Emergency Preparedness |
| ExPlan | Exercise Plan |
| FL | Finger Lakes |
| FOUO | For Official Use Only |
| FPC | Final Planning Conference |
| GR | Greater Rochester |
| HSEEP | Homeland Security Exercise and Evaluation Program |
| IPC | Initial Planning Conference |
| IT | Information Technology |
| MPC | Middle Planning Conference |
| NY | New York |
| NYSDHSES | New York State Division of Homeland Security and Emergency Services |
| NYSDOH | New York State Department of Health |
| PA | Pennsylvania |
| POC | Point of Contact |
| RACES | Radio Amateur Civil Emergency Service |
| SimCell | Simulation Cell |
| SOEM | State Office of Emergency Management (NYSDHSES) |
| STARTEX | Start of Exercise |
| U of R | University of Rochester |
| VIP | Very Important Person |
| WNY | Western New York |
| WRECK IT | Western Region Emergency Communications, Knowledge, and Information Tests |
| WR | Western Region |